## Slide 1
Your yellow belt project storyboard template
A guide on how to create your project storyboard
David Pepin, knowledge transfer manager
Operational excellence

## Slide 2: Storyboard: What’s Required
Complete the Green Belt Storyboard Checklist (see following pages)
Tell Your Story Succinctly
  Use a maximum of 25 Slides (plus a title page) to describe your project
  Make sure the flow of the project story is logical
  Clearly illustrate your analysis and how solutions/countermeasures address the root causes
  Let visuals (graphs, charts, maps, pictures etc.) do most of the work
Use the Tools Wisely
  Show that you understand the DMAIC method by selecting the right tools for the right reasons during each Phase
  Add a “Key Take Away” to each slide to make it clear to the reader what you learned at each step
Label Your Graphs Clearly
  Title all graphs & charts, label each axis and indicate the time frame of the data and the axes names/units for each chart (along with the “Key Take Away”)
Be Clear About Your Analysis
  Describe all root cause hypotheses along with how you verified or disproved each one
Show Measureable Improvement
  Document each reduction in waste, time or defects and show "before" and "after” proof
See Yellow Belt Storyboard Checklist for Required Contents
Yellow Belt Project Storyboard Template | Reference - Delete

## Slide 3: Storyboard Checklist
To replace with your own templates:
Use screenshots – or
Mac: Copy and paste “Special” with HTML format
PC: Copy and paste, select “Keep Source Formatting”
Does not count toward total slide maximum

## Slide 4: Storyboard Checklist (part 2)
Does not count toward total slide maximum

## Slide 5: Executive Summary
Key Take Away: The project was a great success! Profits are up, customers are happier and so is the Bahama Bistro staff!
Required

## Slide 6
Define Phase
Does not count toward total slide maximum

## Slide 7: Project Charter
Key Take Away: Excellent buy-in – project is worth doing.
Required

## Slide 8: SIPOC
Key Take Away: The scope of the project is from the moment we receive the customer order to the moment they receive their lunch order.
Required

## Slide 9: “As-Is” Detailed Map Segment
Key Take Away: The team learned about the wait during the lunch order process walk – customers were not happy!
Required – Pick one or more detailed maps

## Slide 10
Measure Phase
Does not count toward total slide maximum

## Slide 11: Data Collection Plan
Key Take Away: This is a Lead Time project so, except for % late, most of the measures are continuous measures of process segment times.
Required

## Slide 12: Baseline – Project Y
Key Take Away: Lots of variation in the process and the average time to serve lunch is 27 minutes which is very high!
Required – Run Chart Display of Baseline

## Slide 13: Baseline – Lunch Order Lead Time
Key Take Away: Customers want delivery in 20 minutes or less, so the lunch delivery process is clearly not capable.
Optional – Additional displays of baseline data

## Slide 14
Analyze Phase
Does not count toward total slide maximum

## Slide 15: Fishbone Diagram
Key Take Away: The biggest areas to analyze further where prep time, sandwich area, packaging and server habits.
Required

## Slide 16: Map Segment Showing Analysis
Key Take Away: Process analysis showed a potential for removing time wasted during packaging.
Required – Insert one or more project-specific maps showing analysis

## Slide 17: “As-Is” Detailed Map Segment
Key Take Away: A 5S effort showed the waste of motion – the exercise included kitchen staff which resulted in increased employee engagement.
Optional – Add additional detailed map

## Slide 18: Map Segment Showing Analysis
Value-Added Flow Analysis |  |  |  |  | 
Name: | Tracy | Process Name: | Lunch Order to Delivery |  | 
Date: | 10-Mar | Time Measured In: | Minutes | Hours | Days
 |  |  | (select units) |  | 
# | Process Step | Step Label (VA, NVA, NVAr) | Value Added Time | NVA & NVA-Required Work Time | NVA - Wait Time
 | Walk the customer order to the kitchen | NVA |  | 2 | 
 | Check if it's readable | NVA |  | 2 | 
 | If not readable, bring back to the waitress | NVA |  | 2 | 
 | Ask the waitress to clarify the order | NVA |  | 2 | 
 | Walk the customer order back to the kitchen | NVA |  | 2 | 
 | Prep cook passes the order to the chef | NVA |  | 2 | 
 | Chef assesses the order | NVA-r |  | 2 | 
 | Ingredients assembled | VA | 2 |  | 
 | Order cooked or prepared | VA | 7 |  | 
 | Order plated | NVA-r |  | 1 | 
 | Order placed on the warmer/staging | NVA |  |  | 1
 | Order waits for pickup | NVA |  |  | 10
 | Waitress picks up order | NVA |  |  | 2
 | Customer Receives the order | VA | 1 |  | 
 |  | Time | % of total |  | 
Total Value-Added Work Time |  | 10 | 26.32% |  | 76
Total Non-Value-Added or NVA-r Work Time |  | 15 | 39.47% |  | 
NVA - Wait Time |  | 13 | 34.21% |  | 
Total Cycle Time |  | 38 | 100.00% |  | 
Key Take Away: Biggest opportunity to remove wait time is the pick-up area - there are also too many steps checking and clarifying the order.
Required – Insert one or more project-specific maps showing analysis

## Slide 19: Root Cause Confirmations
Key Take Away: Data confirmed most of the hypotheses except for cook time and server – neither contributed significantly to late lunch orders.
Required

## Slide 20
Improve Phase
Does not count toward total slide maximum

## Slide 21: Selected Solutions
Solution Selection Matrix |  |  |  |  |  |  | 
Project Goal | Please rank each solution for each criteria by using the 1-5 Scale as indicated below |  |  |  |  |  | 
Enter Goal Statement below: (As stated on Project Charter) |  |  |  |  |  |  | 
Deliver lunch orders in less than 30 minutes by end of May | Very Low (less good) |  | Moderate |  | Very High (best) |  | 
 | 1 | 2 | 3 | 4 | 5 |  | 
Potential Solution (Provide Brief Description) | Potential to Meet Goal | Positive Customer Impact | Cost to Implement (1 = $$$ & 5 = $) | Stakeholder Buy-in | Time to Implement (1 = Long 5 = Quick) | Total Score | Implement? Yes/No
Weighted Criteria | 10 | 9 | 8 | 7 | 5 |  | 
Don't include condiments with takeout | 5 | 3 | 4 | 4 | 5 | 162 | Yes
Change vendors | 5 | 4 | 2 | 3 | 3 | 138 | Yes
Cross-Train servers and cashiers | 4 | 4 | 2 | 5 | 2 | 137 | Yes
Rebuild Take-out assembly space | 4 | 3 | 1 | 3 | 2 | 106 | Yes
Add new labled bins for condiments | 4 | 5 | 5 | 4 | 5 | 178 | Yes
Reduce the takeout menu | 3 | 3 | 3 | 3 | 2 | 112 | No
Key Take Away: There was no buy-in to reduce the take-out menu so the team focused first on cross-training which resulted in better staff relationships.
Required – Can also use Impact Effort Matrix

## Slide 22: “To Be” Map Segment
Key Take Away: Process changes including cross-training and 5Sing the Sandwich prep area made the difference.
Optional – Add Additional maps showing improvement

## Slide 23: “To Be” Map Segment
Key Take Away: The “U” shape wastes the least amount of motion. Every item is within hands reach with the new setup.
Required – Insert one or more project-specific maps showing improvement

## Slide 24: Run Chart Showing Improvement
Key Take Away: Improvements had a big impact on lunch order Lead Time!
Required – Run Chart showing before and after improvement

## Slide 25
Control Phase
Does not count toward total slide maximum

## Slide 26: Control Chart Showing Improvement
Key Take Away: Improvements had a big impact on lunch order Lead Time!
Required – Control Chart showing before and after improvement

## Slide 27: Monitoring & Response Plan
Key Take Away: Good mix of an input and a process measure as predictors of the output measure, Lunch Order Lead Time, for ongoing monitoring
Required

## Slide 28: Project Closure
Key Take Away: Ended up with some hard savings/increase in revenue and the Process Owner is thrilled. Ready for the next cycle of improvement!
Required

## Slide 29: Appendix
Insert Key Words on first slide of Appendix
Include supporting documentation, process maps and data charts provide evidence of tool applications or helpful project background
Add the “Key Take Away” for each slide
Visit opex.ubc.ca for More Lean Six Sigma Resources!
Does not count toward total slide maximum

## Slide 30: Keywords (Specific to Your Industry)
List all words and acronyms that are specific to your industry and key to understanding your project
Provide a brief description or definition of each term
List in alphabetical order
Keep in mind that this document will be viewed by those who are not in your industry or familiar with your process or industry
Does not count toward total slide maximum

## Slide 31: Keywords (Specific to Bahama Bistro)
Order Lead Time: Total cycle time from the moment the customer places their order to the moment they receive their food.
Lunch Time: Key lunch ordering hours from 11am to 2pm
Customers: Business people and vacationers
Packaging Process: All tasks related to placing food into take-out containers, selecting utensils, napkins and condiments and then placing them all into a bag
Stock Items: All raw food items and food packaging items
Condiments: Mini-bottles of hot sauce, limes, salt and pepper
Does not count toward total slide maximum