## Prioritization
PROJECT PRIORITIZATION MATRIX
INSTRUCTIONS: Assess and compare up to 3 projects at the same time. For each project, score all criteria using the scales provided. Note that each criteria has a different weight. Evaluate and compare the results using all the charts provided. If you have any questions about this form, please contact us at operational.excellence@ubc.ca. | [5 empty] | Version 1.4, July 19 2023
[6 empty] | Project 1 |  | Project 2 |  | Project 3
Criteria | Weight 1~5 | Lower priority |  |  | Higher priority
|  | 0 | 3 | 6 | 9 | Score | Comments | Score | Comments | Score | Comments
1. Link to UBC strategic goals What is the strategic fit? | 5 | No linked to any UBC strategy | Link to one strategy | Link to two strategies | Link to three or more strategies
2. Net financial savings generated | 5 | None | Up to CAD 300 k | CAD 301 ~ 600 k | CAD 601 k and above
3. Other benefits / efficiencies: 1 - Increased customer satisfaction 2 - Productivity 3 - Improved morale 4 - Smoother operations 5 - Safer working environment 6 - Greater flexibility/responsiveness 7 - Eliminate defects 8 - Improved quality 9 - Reduced lead time | 5 | None are true | Up to 3 are true | 4 ~ 6 are true | 7 ~ 9 are true
4. Required service / product (any of these true) 1 - Mandatory (Compliance/Legal) 2 - Impacts Core Services 3 - Other services depend on it | 5 | None are true | One is true | Two are true | All are true
5. Value to the customer Does the project enhance the service to the customer? | 4 | No additional value | Low additional value | Medium additional value | High additional value
6. Importance to risk mitigation or impact if not doing anything | 5 | No additional risk if not offered | Low risk if not offered | Medium risk if not offered | High risk if not offered
7. Process complexity | 3 | High Complexity | Average Complexity | Little complexity | Not complex
8. Frequency of process execution | 3 | Once a month or longer | Once a week | Once a day | Several times a day
9. Degree of impact from change Does the change impact 1 team or the entire UBC? How many employees are impacted in total? Are all employee groups impacted the same or differently? What is the degree of change in terms of people (job roles, pay), process, technology, and organization? | 3 | Insignificant degree of impact | Small degree of impact | Medium degree of impact | High degree of impact
10. Organizational change capacity and maturity Do employees agree with the change? Have past changes been successful and perceived as positive? How many concurrent changes are ongoing? Are leaders, managers, and employees proficient in change? | 3 | Organization is resistant to change | Organization has low change capacity | Organization has medium change capacity | Organization has high change capacity
11. Readiness to launch: leadership / sponsorship Is there a sponsor with authority over people, resources, and funds to make decisions? Can the sponsor commit time to actively participate in the project? | 5 | There is no sponsor | Sponsor has limited authority and time | Sponsor has adequate authority and time | Sponsor has exceptional authority and time
12. Readiness to launch: project management Is a project manager assigned, and has the PM create a project charter, detailed plan, and secured all resources required? | 3 | There is no project manager | Project plan has started | Project plan is ready to be reviewed | Project plan has been approved
13. Readiness to launch: change management Is there a structure change management plan, linked with the project plan? If this is a complex change, do you have dedicated change management resources to support the project? | 3 | There is no change manager | Change management plan has started | Change management plan is ready to be reviewed | Change management plan has been approved
TOTAL SCORE (Max of 117) | [5 empty] | 0 |  | 0 |  | 0
TOTAL WEIGHTED SCORE (Max of 468) | [5 empty] | 0 |  | 0 |  | 0
Prepared by: | [5 empty] | Date:
Operational Excellence Website | [5 empty] | Operational Excellence Team
Where to Download this Template | [5 empty] | Contact Us
Note on H3: Insert project name below.
Note on J3: Insert project name below.
Note on L3: Insert project name below.
Note on B7: How does this project aligns with UBC's strategy? Mention the specific strategy(ies) that this project is linked to: CORE AREA 1 - PEOPLE AND PLACES Strategy 1: Great People. Attract, engage and retain a diverse global community of outstanding students, faculty and staff Strategy 2: Inspiring Spaces. Create welcoming physical and virtual spaces to advance collaboration, innovation and community development Strategy 3: Thriving Communities. Support the ongoing development of sustainable, healthy and connected campuses and communities Strategy 4: Inclusive Excellence. Cultivate a diverse community that creates and sustains equitable and inclusive campuses Strategy 5: Systems Renewal. Transform university-level systems and processes to facilitate collaboration, innovation and agility CORE AREA 2 - RESEARCH EXCELLENCE Strategy 6: Collaborative Clusters. Enable interdisciplinary clusters of research excellence in pursuit of societal impact Strategy 7: Research Support. Strengthen shared infrastructure and resources to support research excellence Strategy 8: Student Research. Broaden access to, and enhance, student research experiences Strategy 9: Knowledge Exchange. Improve the ecosystem that supports the translation of research into action Strategy 10: Research Culture. Foster a strong and diverse research culture that embraces the highest standards of integrity, collegiality and service CORE AREA 3 - TRANSFORMATIVE LEARNING Strategy 11: Education Renewal. Facilitate sustained program renewal and improvements in teaching effectiveness Strategy 12: Program Redesign. Reframe undergraduate academic program design in terms of learning outcomes and competencies Strategy 13: Practical Learning. Expand experiential, work-integrated and extended learning opportunities for students, faculty, staff and alumni Strategy 14: Interdisciplinary Education. Facilitate the development of integrative, problem-focussed Strategy 15: Student Experience. Strengthen undergraduate and graduate student communities and experience learning CORE AREA 4: LOCAL AND GLOBAL ENGAGEMENT Strategy 16: Public Relevance. Deepen the relevance and public impact of UBC research and education Strategy 17: Indigenous Engagement. Support the objectives and actions of the renewed Indigenous Strategic Plan Strategy 18: Alumni Engagement. Reach, inspire and engage alumni through lifelong enrichment Strategy 19: Global Networks. Build and sustain strategic global networks, notably around the Pacific Rim, that enhance impact Strategy 20: Coordinated Engagement. Co-create with communities the principles and effective practices of engagement, and establish supporting infrastructure

## Project Dashboard (hidden)
PROJECT DASHBOARD
METRICS | Weight | Project 1 |  | Project 2 |  | Project 3
|  | 0 |  | 0 |  | 0
|  | Score | Weighted Score | Score | Weighted Score | Score | Weighted Score
1. Strategic fit | 5 | 0 | 0 | 0 | 0 | 0 | 0
2. Net financial savings | 5 | 0 | 0 | 0 | 0 | 0 | 0
3. Other benefits/efficiencies | 5 | 0 | 0 | 0 | 0 | 0 | 0
4. Required service/product | 5 | 0 | 0 | 0 | 0 | 0 | 0
5. Customer value | 4 | 0 | 0 | 0 | 0 | 0 | 0
6. Importance to risk mitigation | 5 | 0 | 0 | 0 | 0 | 0 | 0
7. Process complexity | 3 | 0 | 0 | 0 | 0 | 0 | 0
8. Frequency of process execution | 3 | 0 | 0 | 0 | 0 | 0 | 0
9. Degree of Impact from change | 3 | 0 | 0 | 0 | 0 | 0 | 0
10. Organizational change capacity | 3 | 0 | 0 | 0 | 0 | 0 | 0
11. Readiness - leadership | 5 | 0 | 0 | 0 | 0 | 0 | 0
12. Readiness - project management | 3 | 0 | 0 | 0 | 0 | 0 | 0
13. Readiness - change management | 3 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL SCORE |  | 0 | 0 | 0 | 0 | 0 | 0
CHANGE MANAGEMENT |  | Score | Adjusted | Score | Adjusted | Score | Adjusted
9. Degree of Impact from change |  | 0 |  | 0 |  | 0
10. Organizational change capacity |  | 0 |  | 0 |  | 0

## Reference Data (hidden)
Score 0~9 | Score 1~5 | Chart Titles
0 | 1 | - Normal Scores
3 | 2 | - Normal Scores
6 | 3 | - Normal Scores
9 | 4 | - Weighted Scores
| 5 | - Weighted Scores
- Weighted Scores

## Change Log (hidden)
# | Date | Feedback Received From | Tab | Section | Change | Approved | Version | Implemented on Website on
1 | 2023-03-31 | Alex Fiuza | All | All | Removed intake form tab since it is now migrated into Smartsheet. Changed prioritization tab and all corresponding charts to allow assessment and vizualization of 3 different projects at the same time. | Yes | 1.3 | 2023-04-03
2 | 2023-07-19 | Alex Fiuza | Change Management Chart |  | Reversed scale (labels only) for change capacity and maturity. | Yes | 1.4 | 2023-07-20
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50